## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original(h) | Effort Plan Updated(h) | Effort Actual(h) | Status
1 | Doctor wants to Log in | Doctor logs in with UID and Password(Athorisation) | High | 10 | 0 | 0 | in Process
2 | Doctor views Patient information | Dctor chooses Patient and reviews Info | High | 30 | 0 | 0 | waiting
3 | Doctor creates a new PD(PatientDossier) | create | High | 30 | 0 | 0 | In Process
4 | Doctor changes Information of a PD(PatientDossier) | update | High | 30 | 0 | 0 | waiting
5 | Doctor deletes access to Information of a PD(PatientDossier) | delete | high | 30 | 0 | 0 | waiting
6 | Doctor views Timeline | View from a Foreign DB | low | 40 | 0 | 0 | waiting

## Backlog Sprint 1 & 2
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Package Structure | Create Packages and structure |  | Katsiaryna | high | 1 | 2 | 3 | done
1.2 | 1 | Login GUI | Create GUI of Login | UI | Jonathan,Melissa | high | 1 | 0 | 4 | done
1.3 | 1 | Login Controller | Implement Login class controller | Controller | Melisa | high | 2 | 0 | 0 | cancelled
1.4 | 1 | DatabaseHandler | Create a DatabaseHandler to handle Login Information(UID, PW) | Database | Manuel | high | 3 | 5 | 7 | done
1.5 | 1 | Authorisation | Compare UID and PW with Info from DB | Controller, DB | Philipp, Manuel | medium | 2 | 2 | 2
1.6 | 1 | Test Login | Testrun | All the above | Philipp | medium | 1 | 1 | 1 | done
1.7 | 1 | Project | Fixing work enviroment |  | Philipp | high | 5 | 3 | 4 | done
Total | [6 empty] | 15 | 13 | 21
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
2.1 |  | Project | Fixing work enviroment |  | Philipp | high | 4 | 6 | 5 | done
2.2 | 2 | Navigator | Create a navigator for changing views | UI | Jonathan,Melisa | high | 2 | 6 | 8 | done
2.3 | 2 | Homeview GUI | Create a HomeView of application | UI | Melissa,Katsiaryna | hight | 2 | 4 | 5 | done
2.4 | 2 | PatientView GUI | Create a new addNewPatient View | UI | Melisa | high | 2 | 2 | 3 | done
2.5 | 2 | Conection of Data, Login | Connect a DatabaseHandler with Login Controller | DB, Controller, UI | Manuel | high | 2 | 2 | 2 | done
2.6 | 2 | Connection of Data, PatientInfo | Transfer data from Class Patient, save them in XML file, deserialize them, make Test | UI, Modeldata, DB | Katsiaryna, Manuel, Philipp, | high | 4 | 6 | 6 | done
2.7 | 2 | AbstractView | Create a class of AbstractView, a superclass for all views | UI | Philipp, Jonathan | medium | 2 |  |  | cancelled
2.8 | 2 | addPatientView | Create a View for giving new Patients data in system | UI | Jonathan, Melisa | medium | 3 | 3 | 4 | done
Total | [6 empty] | 21 | 29 | 33
2. Sprint
1. Sprint

## Backlog Sprint 3
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
3.1 | 3 | Homeview with Patients | Homeview with a list of all patients | UI | Katharina, Melisa | high | 8 | 5 | 7 | done
3.2 | 3 | Database Connection HomeView | Patients in DB are shown in Homeview | DB | Katharina, Melisa | high | 8 | 5 | 4 | done
3.3 | 3 | Patientview | all Informations about a selected patient with CV, TL | UI | Katharina, Melisa,Manuel | high | 4 | 5 | 6 | done(in a different way
3.3 | 3 | Database Connection Patientview | all Informations about a selected patient with CV, TL | DB | Katarina, Melisa | high | 4 | 2 | 2 | done
3.4 | 3 | CV View | CV View : Doctor can add specific information about the patient | View | Jonathan | medium | 6 | 5 | 5 | done
3.5 | 3 | TL View | Timelineview with all informations | View | Jonathan | medium | 2 | 2 | 2 | done
3.6 | 3 | State Pattern | Connecting the existing views | State Pattern | Philipp | medium | 4 | 3 | 3 | done
3.7 | 3 | Find function | Functiom for looking for Patients in DB | DB | Manuel | high | 7 | 8 | 8 | done
Total | [6 empty] | 43 | 35 | 37
3. Sprint

## Burn-Down-Chart
| Sprint 1 | Sprint 2 | Sprint 3
Planned | 15 | 21 | 43 | 79
Updated | 13 | 29 | 35 | 77
Actual | 21 | 33 | 37 | 91
| Sprint 1 | Sprint 2 | Sprint 3
Planned | 64 | 43 | 0
Updated | 64 | 35 | 0
Actual | 70 | 37 | 0
Time