## Product Backlog
ID | Story Name | Description | Priority | Effort Plan Original(h) | Effort Plan Updated(h) | Effort Actual(h) | Status
1 | Doctor wants to Log in | Doctor logs in with UID and Password(Athorisation) | High | 10 | 0 | 0 | in Process
2 | Doctor views Patient information | Dctor chooses Patient and reviews Info | High | 30 | 0 | 0 | waiting
3 | Doctor creates a new PD(PatientDossier) | create | High | 30 | 0 | 0 | In Process
4 | Doctor changes Information of a PD(PatientDossier) | update | High | 30 | 0 | 0 | waiting
5 | Doctor deletes access to Information of a PD(PatientDossier) | delete | high | 30 | 0 | 0 | waiting
6 | Doctor views Timeline | View from a Foreign DB | low | 40 | 0 | 0 | waiting

## Sprint Backlog
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
1.1 | 1 | Package Structure | Create Packages and structure |  | Katsiaryna | high | 1 | 2 | 3 | done
1.2 | 1 | Login GUI | Create GUI of Login | UI | Jonathan | high | 1 | 0 | 0 | done
1.3 | 1 | Login Controller | Implement Login class controller | Controller | Melisa | high | 2 | 0 | 0 | cancelled
1.4 | 1 | DatabaseHandler | Create a DatabaseHandler to handle Login Information(UID, PW) | Database | Manuel | high | 3 | 3 | 3 | done
1.5 | 1 | Authorisation | Compare UID and PW with Info from DB | Controller, DB | Philipp, Manuel | medium | 2 | 2 | 2 | done
1.6 | 1 | Test Login | Testrun | All the above | Philipp | medium | 1 | 1 | 1 | done
ID | Sprint | Name | Description | Components | Owner | Priority | Effort Plan Original | Effort Plan Updated | Effort Actual | Status
2.1 |  | Project | Fixing work enviroment |  | Philipp | high | 4 |  |  | In process
2.2 | 2 | Navigator | Create a navigator for changing views | UI | Jonathan | high | 2 |  |  | In Process
2.3 | 2 | Homeview GUI | Create a HomeView of application | UI | Katsiaryna | hight | 2 | 2 | 2 | In process
2.4 | 2 | PatientView GUI | Create a new addNewPatient View | UI | Melisa | high | 2 |  |  | In process
2.5 | 2 | Conection of Data, Login | Connect a DatabaseHandler with Login Controller | DB, Controller, UI | Manuel | high | 2 |  |  | In process
2.6 | 2 | Connection of Data, PatientInfo | Get data from database, save them in Class Patient, move them to PatientView | UI, Modeldata, DB | Katsiaryna, Manuel, Philipp, | high | 4 |  |  | waiting
2.7 | 2 | AbstractView | Create a class of AbstractView, a superclass for all views | UI | Philipp, Jonathan | medium | 2 |  |  | waiting
2.8 | 2 | addPatientView | Create a View for giving new Patients data in system | UI | Jonathan, Melisa | medium | 3 |  |  | waiting
2.Sprint